## ProductBacklog
Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | Type
fdasf fdaf
1 | Standard document | High | PECUNIABANK:001 | Design Documentation for Backend application | Ganesh | Ganesh | Average | Low | Non-Functional | Design is fullfilled agaist Business requirement
2 | Standard document | High | PECUNIABANK:002 | Bootstraping the project | Ganesh | Ganesh | Low | High | Non-Functional | Checking Against the Application Setup and ensure the equired dependencies and run the main code and check the server is tarted without errors
3 | Standard document |  | PECUNIABANK:003 | Account | Ganesh | Ganesh |  | High | Functional | Designing the user cases against Business requirement
4 | Standard document | High | PECUNIABANK:004 | Transaction | Ganesh | Ganesh | Complex | HIgh | Functional | Designing the user cases against Business requirement
5 | Standard document | High | PECUNIABANK:005 | Loan | Ganesh | Ganesh | Complex | High | Functional | Designing the user cases against Business requirement
6 | Standard document | High | PECUNIABANK:006 | Passbook | Ganesh | Ganesh | Complex | High | Functional | Designing the user cases against Business requirement
| Work session | High | PECUNIABANK:007 | Populating test data in database | Ganesh | Ganesh | Simple | Low | Non-Functional
7 | Work session | High | PECUNIABANK:008 | Testing all the functionalities in postman whether all are working or not | Ganesh | Ganesh | Complex | High | Non-Functional
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41

## SprintBacklog
Product Backlog ID | User Story ID | User Story Task Step Number | Task Step Description |  | Assigned Date | Original Estimate | Adjustment Estimate | Status | Actual Effort
1 | PECUNIABANK:001 | 1 | Entity Class Design |  |  | 2 hrs | 1 hr
|  | 2 | Use case diagram |  |  | 1hr | 0.5 hr
|  | 3 | Sequence Diagram |  |  | 1hr | 0.5hr
|  | 4 | Class Layer diagram |  |  | 2 hrs | 1 hr
|  | 5 | Class Diagram |  |  | 2 hrs
|  | 6 | TestCaseTemplate |  |  | 2 hrs | 1hr | Completed | 2hrs
2 | PECUNIABANK:002 | 1 | Creating a Spring boot starter project |  |  | 1 hr | 0.5 hrs
|  | 2 | Adding dependencies in Pom.xml and initializing it |  |  | 1 hrs | 0,5 hrs
|  | 3 | Adding server, jpa and logging properties in application.properties |  |  | 1 hrs | 0,5 hrs
3 | PECUNIABANK:005 | 1 | Loan Request | DAO |  | 3 hrs | 1.5 hrs
|  |  |  | SERVICE |  | 3 hrs | 1.5 hrs
|  |  |  | CONTROLLER |  | 3 hrs | 1.5 hrs
|  | 2 | Loan Disbursal | DAO |  | 3 hrs | 1.5 hrs
|  |  |  | SERVICE |  | 3 hrs | 1.5 hrs
|  |  |  | CONTROLLER |  | 3 hrs | 1.5 hrs
4 | PECUNIABANK:007 | 1 | Populating the test data in database |  |  | 3 hrs | 1 hr
5 | PECUNIABANK:008 | 1 | Testing the functionalites in postman | DAO, SERVICE, CONTROLLER